Sample Evaluation Timeline

| Month | Project Goal | Related Objective | Activity | Expected Completion Date | Person Responsible |
| --- | --- | --- | --- | --- | --- |
| 1-12 | Continue to conduct process evaluation in Florida of APYA/STREET Smart programs. | Monitor the operations of APYA/STREET Smart programs. | Conduct site visits to review and discuss program operations. | October 2005 April 2006 | Bob Smith Tim Black |
| 1-12 | Continue to conduct outcome evaluation. | Complete data collection for experimental group. | Work with Community Specialists to complete STREET Smart exit data for experimental group. | May 2006 | Community Specialists/ Tim Matthews |
|  |  | Finalize data collection procedures for control group. | Extract and analyze JJIS data on demographics and service/placement history. | December 2006 | NCCD Research Team |
|  |  | Access and analyze information sources for follow-up data collection on outcome measures for experimental and control groups | Receive second annual data extract from DJJ for conducting recidivism analysis. | December 2006 | Bob Smith |
|  |  |  | Receive second annual employment and education data extract from FETPIP. | February 2007 | Bob Smith Tim Black |
|  |  |  | Receive second annual educational outcome data extract from DOE | April 2007 | Bob Smith Tim Blacks |

| Month | Project Goal | Related Objective | Activity | Expected Completion Date | Person Responsible |
| --- | --- | --- | --- | --- | --- |
|  |  | Conduct sample case tracking and follow-up interviewing. | Initiate and complete tracking and follow-up component of the evaluation for 710 cases. | September 2007 | Subcontractor |
|  |  | Develop and implement initial plans for data analysis and reporting. | Conduct analysis of FETPIP data. | April 2007 | NCCD Research Team |
|  |  |  | Conduct analysis using DOE/EDW data. | June 2007 | NCCD Research Team |
|  |  |  | Conduct analysis and reporting for recidivism using DJJ data extract. | February 2007 | NCCD Research Team |
|  |  | Maintain privacy and protection of human subjects’ certifications | Complete all privacy and certifications as required. | Ongoing | Bob Smith |